## Sheet1
	April		May
	29	30	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26
GENERAL
	Implement filtering of malformed inputs
								Implement cleanup for comment-post mapping
	Conceptualize configuration using files

T1
	Create integration test							BUFFER

T2
	Enrich event streams with static data
	Enrich user embedding with static data
								Create integration test					BUFFER

T3
	Implement ensemble decision
	Implement rolling statistics operator
	Feature: Timespan
								Feature: Associated Tags (Count)
								Feature: Interacting Users
								Feature: Interactions Ratio
								Feature: Post Activeness (Duration)
	Feature: Post/Comment Contents
								Create integration test					BUFFER

OUTPUT
	Connect pipelines to Kafka sinks
								Implement visualization frontend